## Instructions
ITC327W Project Progress and Contribution Workbook
Use this workbook throughout the semester. Update it after each project phase and submit the same workbook again so that progress can be tracked over time.
Sheet | Purpose | Evidence and Accountability Rules
Project Overview | Enter the group and project details. The dashboard summarises task progress automatically. | 1 | Every student must be assigned meaningful work in Microsoft Project.
Task Progress | Record planned and completed tasks, responsible students, dates, status, percentage completed and evidence. | 2 | Completed work must be supported by evidence such as GitHub activity, meeting records, document sections, screenshots or stakeholder communication.
Individual Contributions | Record the work personally completed by each student. Every entry must have evidence. | 3 | GitHub commits are not the only evidence. Planning, interviewing, documentation, coordination and quality review also count.
Stakeholder Engagement | Record meetings, calls and emails with the stakeholder and the main outcomes. | 4 | Do not record work as completed by a student when it was completed by someone else.
Challenges & Actions | Record project challenges, their effect and the corrective action taken. | 5 | Do not place passwords, API keys, identity numbers, private contact details or confidential records in this workbook or on GitHub.
Phase Summary | Provide a short summary of the phase, including achievements, outstanding work and participation concerns. | 6 | The confidential individual peer evaluation must be completed separately on Blackboard.
Group Reflection | Complete one shared reflection after each phase. Be honest and specific.
Recommended Update Points
|  | Unit 1 / Phase 1 | Planning, stakeholder engagement, requirements and initial SRS
|  | Phase 2 | Architecture, UML, ERD and interface design
|  | Phase 3 | Development, integration, testing and demonstration
|  | Final | Overall project summary and final reflection

## Project Overview
Project Overview and Progress Dashboard
Project Information | Group Response | Task Status | Count
Group name or number | Group 5 | Completed | 11
Project title | Lenyora Primary School Digital Application System | In Progress | 0
Stakeholder or organisation | Lenyora Primary School | Not Started | 0
Group mentor | Mr. T. Mokoduwe | Delayed | 0
Reporting phase | Phase 1 | Blocked | 0
Reporting period | 17 August 2026 - 26 August 2026 | Overdue | 0
Overall status | In Progress
Overall % complete | 91.67% | Contribution Summary | Count
Main achievement | Successfully completed and confirmed initial SRS with stakeholder approval. Conducted stakeholder interview. Established GitHub repository and Supabase project. | Contribution entries | 12
Main challenge | Coordinating schedules for the stakeholder interview and gathering complete subject listings per grade from the school administration. | Verified entries | 12
Next planned activity | Begin system architecture design, UML diagrams, and database schema development for Phase 2 | Unverified entries | 0
|  | Stakeholder engagements | 0

## Task Progress
Task Progress Tracker
Task ID | Reporting Phase | Activity | Task Description | Assigned Student | Start Date | Due Date | Status | % Complete | Evidence / Link | Verified by Group | Lecturer Comment | Progress Flag
U1-01 | Unit 1 / Phase 1 | Activity 1.1 | Identify and confirm the external stakeholder |  | 17/08/2026 | 26/08/2026 | Completed | 100 |  | Yes |  | Completed
U1-02 | Unit 1 / Phase 1 | Activity 1.1 | Document the current process and problem |  | 18/08/2026 | 26/08/2026 | Completed | 100 |  | No |  | Completed
U1-03 | Unit 1 / Phase 1 | Activity 1.1 | Define the project aim, objectives and scope |  | 20/08/2026 | 26/08/2026 | Completed | 100 |  | No |  | Completed
U1-04 | Unit 1 / Phase 1 | Activity 1.2 | Prepare stakeholder interview questions |  | 20/08/2026 | 26/08/2026 | Completed | 100 |  | No |  | Completed
U1-05 | Unit 1 / Phase 1 | Activity 1.2 | Conduct and document the stakeholder interview |  | 24/08/2026 | 26/08/2026 | Completed | 100 |  | No |  | Completed
U1-06 | Unit 1 / Phase 1 | Activity 1.3 | Compile the initial SRS |  | 25/08/2026 | 26/08/2026 | Completed | 100 |  | No |  | Completed
U1-07 | Unit 1 / Phase 1 | Activity 1.3 | Create the initial Microsoft Project schedule |  | 26/08/2026 | 26/08/2026 | Completed | 100 |  | No |  | Completed
U1-08 | Unit 1 / Phase 1 | Activity 1.3 | Create and configure the GitHub repository |  | 26/08/2026 | 26/08/2026 | Completed | 100 |  | No |  | Completed
U1-09 | Unit 1 / Phase 1 | Activity 1.3 | Create the initial Supabase project |  | 26/08/2026 | 26/08/2026 | Completed | 100 |  | No |  | Completed
U1-10 | Unit 1 / Phase 1 | Activity 1.3 | Complete the progress report and contribution record |  | 26/08/2026 | 26/08/2026 | Completed | 100 |  | No |  | Completed
U1-11 | Unit 1 / Phase 1 | Activity 1.3 | Complete the Unit 1 group reflection |  | 26/08/2026 | 26/08/2026 | Completed | 100 |  | No |  | Completed
Formulas:
Progress Flag = IF([Task Description]="","",IF([Status]="Completed","Completed",IF([Status]="Blocked","Blocked",IF([Status]="Delayed","Delayed",IF(AND([Due Date]<>"",[Due Date]<TODAY(),[Status]<>"Completed"),"Overdue","On Track")))))

## Individual Contributions
Individual Contribution Record
Student Name | Student Number | Reporting Phase | Activity | Assigned Responsibility | Work Personally Completed | Date Completed | Hours Spent | Evidence / Link | Verified by Group | Verification Date | Notes
M.N Matla | 216009568 | Phase 1 | Activity 1.1 | Project Lead / Stakeholder Contact | Identified and confirmed stakeholder. Organized the meeting and obtained signed agreement. | 17/08/2026 | 1.5 |  | Yes
S.M Nkosi | 222020350 | Phase 1 | Activity 1.1 | Process Documentation | Documented the current manual process and problem statement. | 18/08/2026 | 2 |  | Yes
All Members |  | Phase 1 | Activity 1.1 | Define project objectives | Drafted project aim, objectives, and scope sections of SRS | 19/08/2026 | 5 |  | Yes |  | -
G.D. Sekhula | 223028212 | Phase 1 | Activity 1.2 | Interview Preparation | Prepared stakeholder interview questions. | 21/08/2026 | 2 |  | Yes |  | -
All Members |  | Phase 1 | Activity 1.2 | Conduct Interview | Explained the purpose of the interview, asked questions, and recorded the stakeholder's responses. | 24/08/2026 | 0.5 |  | Yes |  | -
All Members |  | Phase 1 | Activity 1.3 | SRS Preparation | Prepared the SRS sections | 25/08/2026 | 9 |  | Yes |  | -
T.H. Mosia | 222040802 | Phase 1 | Activity 1.3 | Microsoft Project Schedule | Created the initial Microsoft Project schedule with all tasks, and timeline. | 26/08/2026 | 5 |  | Yes |  | -
L. Kayane | 222002417 | Phase 1 | Activity 1.3 | Supabase Creation | Created Supabase project. | 26/08/2026 | 0.5 |  | Yes |  | -
L. Kayane | 222002417 | Phase 1 | Activity 1.3 | GitHub Repository | Created and configured GitHub repository. Added README, invited members, and set up documentation folder. | 26/08/2026 | 1 |  | Yes
All Members |  | Phase 1 | Activity 1.3 | Progress Workbook | Completed the Project Progress Workbook with all project details and evidence links. | 26/08/2026 | 3 |  | Yes
All Members |  | Phase 1 | Activity 1.3 | Completed Group Reflection | Completed the group reflection | 26/08/2026 | 1 |  | Yes
All Members |  | Phase 1 | Activity 1.3 | SRS Review | Completed the SRS document | 26/08/2026 | 2 |  | Yes

## Stakeholder Engagement
Stakeholder Engagement Record
Date | Reporting Phase | Type of Engagement | Purpose | Students Present | Stakeholder Present / Role | Main Findings | Action Required | Evidence / Link
17/08/2026 | Phase 1 | Site Visit | Confirmed stakeholder and obtain letter of agreement. | M.N Matla | Head of department, Lenyora Primary School | School confirmed the need for a digital application system. Key features needed: online applications, announcements, subject listings, and status tracking. | Document the current process and problem statement.
24/08/2026 | Phase 1 | Meeting | Gather detailed requirements for the system. Understand stakeholder's needs. | All Members | Head of Department, Lenyora Primary School | Parents miss the opening and closing dates for the applications. Parents frequently ask about subjects per grade. Paper forms are often lost. | Preparing the SRS documentation

## Phase Summary
Phase Progress Summary
Summary Information | Group Response | Phase Completion Checklist
Reporting phase | Phase 1 | Initial or updated SRS completed | Yes
Reporting period | 17 August 2026 - 26 August 2026 | Progress report updated | Yes
Overall phase status | Completed | Individual contributions recorded | Yes
What was completed during this phase? | Successfully identified and confirmed the external stakeholder (Lenyora Primary School) Conducted stakeholder interview and documented findings Defined project aim, objectives, and scope Completed the initial SRS document Created initial Microsoft Project schedule Set up GitHub repository with all group members Created initial Supabase project Completed the progress workbook and individual contribution records Completed group reflection | Stakeholder engagement recorded | Yes
What remains incomplete? | NONE | Challenges and actions updated | Yes
Why is it incomplete? | N/A | Group reflection completed | Yes
Which contributions were particularly important? | Stakeholder engagement and agreement. SRS compilation. Supabase setup and GitHub configuration. | Microsoft Project updated | Yes
Were there participation concerns? | No major participation concerns. All group members actively contributed to their assigned tasks. Good communication and collaboration observed throughout the phase. | GitHub evidence available | Yes
What will the group improve in the next phase? | Earlier scheduling of technical tasks to allow buffer time More proactive stakeholder follow-up | Confidential peer check completed | No
Main priority for the next phase

## Challenges & Actions
Challenges and Corrective Actions
Date Identified | Reporting Phase | Challenge | Effect on Progress | Corrective Action | Responsible Student | Target Date | Status
21/08/2026 | Phase 1 | Our first stakeholder's needs did not align with our project requirements as per the module. | Slight delay in scheduling a meeting with the new stakeholder to collect the requirements. | Managed to schedule the meeting. | All members |  | Resolved
25/08/2026 | Phase 1 | Group member had technical issues with GitHub repository access. | Temporary block on collaborative work. | Re-sent invitation links and provided GitHub setup documentation. Verified access resolved. | L. Kayane |  | Resolved
26/08/2026 | Phase 1 | Misunderstanding about SRS formatting and structure requirements. | Required additional time to reformat document. | Reviewed sample SRS documents. Reorganized document structure accordingly. | S.M. Nkosi, G.D Sekhula |  | Resolved
25/08/2026 | Phase 1 | Used the online microsoft project for scheduling instead of the project professional app. | It was a slight setback as it took too much time to start the new one on the app. | We started scheduling using the project professional app. | T.H Mosia, M.N Matla |  | Resolved

## Group Reflection
Group Reflection
Reflection Information | Group Response | Reflection Guidance
Reporting phase | Phase 1 | Length | Approximately 300–400 words in total.
Project title | School Digital Application System | Focus | Discuss the group’s actual experience, not the activity instructions.
Most important learning from this phase | The most important learning was understanding the critical importance of effective stakeholder engagement. The interview with the head of department revealed that despite having basic technology infrastructure, the school's processes were still heavily manual. We learned that successful systems require not just good code, but deep understanding of user needs and organizational workflows. | Honesty | Identifying a genuine challenge will not disadvantage the group when an improvement action is provided.
What went well and why? | Stakeholder meeting went well because we prepared thoroughly, developed relevant interview questions, and the stakeholder's responses were clear. | Evidence | Ensure that claims about participation agree with the contribution record, Microsoft Project and GitHub.
What was difficult and why? | Gathering the project requirements due to changing our stakeholder. | Research use | Student work may only be used for research after the required ethical approval and consent processes.
How were tasks divided among members? | M.N Matla(Project Lead): Stakeholder management. L. Kayane :Created Github and Supabase. G.D. Sekhula:Prepared interview questions. T.H. Mosia: Created microsoft project. S.M Nkosi: Documented processes and problem statement
Did all members contribute fairly? Explain. | Yes, all members contributed fairly and consistently. Each member completed their assigned responsibilities on time and participated actively in group discussions and meetings.
How did the group handle disagreements or delays? | We worked tirelessly to ensure that we make up for lost time.
What did the group learn from the stakeholder? | Application processing is currently a major administrative burden for school staff Trust and reliability are crucial - the system must work consistently and be simple to use
Improvement action 1 for the next phase | Implement more proactive stakeholder communication - Schedule regular checkpoints (weekly brief updates) to ensure alignment and prevent last-minute information requests.
Improvement action 2 for the next phase | Implement more proactive stakeholder communication - Schedule regular checkpoint to ensure alignment and prevent last-minute information requests.
Priority for the next phase