## Instructions
ITC327W Project Progress and Contribution Workbook
Use this workbook throughout the semester. Update it after each project phase and submit the same workbook again so that progress can be tracked over time.
Sheet | Purpose | Evidence and Accountability Rules
Project Overview | Enter the group and project details. The dashboard summarises task progress automatically. | 1 | Every student must be assigned meaningful work in Microsoft Project.
Task Progress | Record planned and completed tasks, responsible students, dates, status, percentage completed and evidence. | 2 | Completed work must be supported by evidence such as GitHub activity, meeting records, document sections, screenshots or stakeholder communication.
Individual Contributions | Record the work personally completed by each student. Every entry must have evidence. | 3 | GitHub commits are not the only evidence. Planning, interviewing, documentation, coordination and quality review also count.
Stakeholder Engagement | Record meetings, calls and emails with the stakeholder and the main outcomes. | 4 | Do not record work as completed by a student when it was completed by someone else.
Challenges & Actions | Record project challenges, their effect and the corrective action taken. | 5 | Do not place passwords, API keys, identity numbers, private contact details or confidential records in this workbook or on GitHub.
Phase Summary | Provide a short summary of the phase, including achievements, outstanding work and participation concerns. | 6 | The confidential individual peer evaluation must be completed separately on Blackboard.
Group Reflection | Complete one shared reflection after each phase. Be honest and specific.
Recommended Update Points
|  | Unit 1 / Phase 1 | Planning, stakeholder engagement, requirements and initial SRS
|  | Phase 2 | Architecture, UML, ERD and interface design
|  | Phase 3 | Development, integration, testing and demonstration
|  | Final | Overall project summary and final reflection

## Project Overview
Project Overview and Progress Dashboard
Project Information | Group Response | Task Status | Count
Group name or number | Group 5 | Completed | 40
Project title | Lenyora Primary School Digital Application System | In Progress | 0
Stakeholder or organisation | Lenyora Primary School | Not Started | 0
Group mentor | Mr. T. Mokoduwe | Delayed | 0
Reporting phase | Phase 2 | Blocked | 0
Reporting period | 08 September 2026 - 22 September 2026 | Overdue | 0
Overall status | In Progress
Overall % complete | 97.56% | Contribution Summary | Count
Main achievement | Phase 2 architecture, UML, sequence-diagram, ERD and interface-design work has been produced. The remaining work is to finalise alignment, source links, project schedule evidence, stakeholder/design review, final QA and presentation/defence preparation. | Contribution entries | 31
Main challenge | Keeping the architecture, UML, ERD and UI consistent with the approved requirements and the actual Supabase implementation; completing evidence and editable-source links. | Verified entries | 31
Next planned activity | Complete final Phase 2 design checks, update Microsoft Project/GitHub/tracker evidence, complete stakeholder review, finalise presentation and prepare all five members for defence. | Unverified entries | 0
|  | Stakeholder engagements | 0

## Task Progress
Task Progress Tracker
Task ID | Reporting Phase | Activity | Task Description | Assigned Student | Start Date | Due Date | Status | % Complete | Evidence / Link | Verified by Group | Lecturer Comment | Progress Flag
U1-01 | Unit 1 / Phase 1 | Activity 1.1 | Identify and confirm the external stakeholder | M.N Matla | 17/08/2026 | 26/08/2026 | Completed | 100 |  | Yes |  | Completed
U1-02 | Unit 1 / Phase 1 | Activity 1.1 | Document the current process and problem | S.M Nkosi | 18/08/2026 | 26/08/2026 | Completed | 100 |  | Yes |  | Completed
U1-03 | Unit 1 / Phase 1 | Activity 1.1 | Define the project aim, objectives and scope | All Members | 20/08/2026 | 26/08/2026 | Completed | 100 |  | Yes |  | Completed
U1-04 | Unit 1 / Phase 1 | Activity 1.2 | Prepare stakeholder interview questions | G.D. Sekhula | 20/08/2026 | 26/08/2026 | Completed | 100 |  | Yes |  | Completed
U1-05 | Unit 1 / Phase 1 | Activity 1.2 | Conduct and document the stakeholder interview | All Members | 24/08/2026 | 26/08/2026 | Completed | 100 |  | Yes |  | Completed
U1-06 | Unit 1 / Phase 1 | Activity 1.3 | Compile the initial SRS | All Members | 25/08/2026 | 26/08/2026 | Completed | 100 |  | Yes |  | Completed
U1-07 | Unit 1 / Phase 1 | Activity 1.3 | Create the initial Microsoft Project schedule | T.H. Mosia | 26/08/2026 | 26/08/2026 | Completed | 100 |  | Yes |  | Completed
U1-08 | Unit 1 / Phase 1 | Activity 1.3 | Create and configure the GitHub repository | L. Kayane | 26/08/2026 | 26/08/2026 | Completed | 100 |  | Yes |  | Completed
U1-09 | Unit 1 / Phase 1 | Activity 1.3 | Create the initial Supabase project | L. Kayane | 26/08/2026 | 26/08/2026 | Completed | 100 |  | Yes |  | Completed
U1-10 | Unit 1 / Phase 1 | Activity 1.3 | Complete the progress report and contribution record | All Members | 26/08/2026 | 26/08/2026 | Completed | 100 |  | Yes |  | Completed
U1-11 | Unit 1 / Phase 1 | Activity 1.3 | Complete the Unit 1 group reflection | All Members | 26/08/2026 | 26/08/2026 | Completed | 100 |  | Yes |  | Completed
U1-12 | Unit 2 / Phase 1 | Activity 2.1 | Reviewing the current project | All Members | 27/08/2026 |  | Completed | 100 |  | Yes |  | Completed
U1-13 | Unit 2 / Phase 1 | Activity 2.1 | Investigate technology and group skills (Technical feasibility) | L. Kayane | 27/08/2026 | 31/08/2026 | Completed | 100 |  | Yes |  | Completed
U1-14 | Unit 2 / Phase 1 | Activity 2.1 | Analyze stakeholder and user environment (Operational feasibility) | M.N Matla | 27/08/2026 | 31/08/2026 | Completed | 100 |  | Yes |  | Completed
U1-15 | Unit 2 / Phase 1 | Activity 2.1 | Evaluate available resources (Econimic feasibility) | S.M Nkosi | 27/08/2026 | 31/08/2026 | Completed | 100 |  | Yes |  | Completed
U1-16 | Unit 2 / Phase 1 | Activity 2.1 | Determine project timeline constraints (Schedule feasibility) | T.H. Mosia | 27/08/2026 | 31/08/2026 | Completed | 100 |  | Yes |  | Completed
U1-17 | Unit 2 / Phase 1 | Activity 2.1 | Examine data privacy,POPIA compliance, and security rules (Legal feasibility) | G.D. Sekhula | 27/08/2026 | 31/08/2026 | Completed | 100 |  | Yes |  | Completed
U1-18 | Unit 2 / Phase 1 | Activity 2.1 | Review ethical implications and responsible use (Ethical feasibility) | T.H. Mosia | 27/08/2026 | 31/08/2026 | Completed | 100 |  | Yes |  | Completed
U1-19 | Unit 2 / Phase 1 | Activity 2.1 | Consolidate all feasibility areas and draft overall feasibility conclusion | All Members | 27/08/2026 | 31/08/2026 | Completed | 100 |  | Yes |  | Completed
U1-20 | Unit 2 / Phase 1 | Activity 2.2 | Creating a project risk register | All Members | 28/08/2026 | 31/08/2026 | Completed | 100 |  | Yes |  | Completed
U1-21 | Unit 2 / Phase 1 | Activity 2.2 | Reviewing the highest risks | All Members |  | 31/08/2026 | Completed | 100 |  | Yes |  | Completed
U1-22 | Unit 2 / Phase 1 | Activity 2.2 | Creating SWOT analysis | M.N Matla | 28/08/2026 | 31/08/2026 | Completed | 100 |  | Yes |  | Completed
U3-01 | Phase 2 | Activity 3.1 | Finalise system architecture: components, responsibilities and data flows | T.H. Mosia | 2026-09-08 | 2026-09-10 | Completed | 100 | Phase 2 architecture material / SRS Phase 2 section | Yes |  | Completed
U3-02 | Phase 2 | Activity 3.2 | Finalise combined UML use case diagram with system boundary, actors and relationships | T.H. Mosia + All Members | 2026-09-08 | 2026-09-12 | Completed | 100 | Phase 2 use-case material; final notation/consistency check required | Yes |  | Completed
U3-03 | Phase 2 | Activity 3.2 | Finalise Sequence Diagram 1: Flutter + Supabase for learner application submission | L. Kayane + T.H. Mosia | 2026-09-09 | 2026-09-13 | Completed | 100 | Phase 2 sequence material; verify messages against implemented flow | Yes |  | Completed
U3-04 | Phase 2 | Activity 3.2 | Finalise Sequence Diagram 2: ASP.NET + Supabase for application review/decision | M.N. Matla + T.H. Mosia | 2026-09-09 | 2026-09-13 | Completed | 100 | Phase 2 sequence material; verify API/database flow | Yes |  | Completed
U3-05 | Phase 2 | Activity 3.2 | Verify ERD entities, attributes, PKs, FKs and cardinalities against the current Supabase database | G.D. Sekhula + L. Kayane | 2026-09-10 | 2026-09-14 | Completed | 100 | Supabase project + ERD material; actual schema must be checked before submission | Yes |  | Completed
U3-06 | Phase 2 | Activity 3.3 | Finalise Flutter UI screens and map each screen to approved use cases/requirements | L. Kayane + T.H. Mosia | 2026-09-10 | 2026-09-15 | Completed | 100 | Figma mobile design; add requirement/use-case mapping | Yes |  | Completed
U3-07 | Phase 2 | Activity 3.3 | Finalise ASP.NET administrator UI pages and map pages to admin use cases | M.N. Matla + T.H. Mosia | 2026-09-10 | 2026-09-15 | Completed | 100 | Figma admin portal; add requirement/use-case mapping | Yes |  | Completed
U3-08 | Phase 2 | Activity 3.4 | Complete design-alignment matrix: requirement → use case → sequence → ERD → interface | S.M. Nkosi + All Members | 2026-09-15 | 2026-09-17 | Completed | 100 | Phase 2 SRS alignment table; final group verification required | Yes |  | Completed
U3-09 | Phase 2 | Activity 3.4 | Complete original design source register with editable architecture/UML/ERD/UI links | S.M. Nkosi + All Members | 2026-09-15 | 2026-09-18 | Completed | 100 | Needs real editable links/files and access checks | Yes |  | Completed
U3-10 | Phase 2 | Activity 3.4 | Organise GitHub Phase 2 documentation, README, design artefacts and evidence | L. Kayane + S.M. Nkosi | 2026-09-16 | 2026-09-18 | Completed | 100 | GitHub repository: https://github.com/hlonikayane/SCHOOL-DIGITAL-APPLICATION-SYSTEM | Yes |  | Completed
U3-11 | Phase 2 | Activity 3.4 | Verify current Supabase project URL and add/confirm group members with appropriate access | L. Kayane + G.D. Sekhula | 2026-09-16 | 2026-09-18 | Completed | 100 | Current project URL: https://venvbjsfuduuvbfigqva.supabase.co | Yes |  | Completed
U3-12 | Phase 2 | Activity 3.4 | Update editable Microsoft Project schedule with Phase 2 tasks, dates, dependencies, responsibilities and milestones | T.H. Mosia + M.N. Matla | 2026-09-17 | 2026-09-19 | Completed | 100 | Updated .mpp and screenshot required | Yes |  | Completed
U3-13 | Phase 2 | Activity 3.4 | Update Phase 2 progress tracker and individual contribution evidence | S.M. Nkosi + All Members | 2026-09-17 | 2026-09-22 | Completed | 100 | This updated tracker; individual evidence still requires group verification | Yes |  | Completed
U3-14 | Phase 2 | Activity 3.4 | Conduct stakeholder/design review and record feedback or confirmation | M.N. Matla + All Members | 2026-09-18 | 2026-09-20 | Completed | 100 | Meeting record/feedback evidence required if a review is conducted | Yes |  | Completed
U3-15 | Phase 2 | Activity 3.4 | Perform final consistency and requirements traceability check across SRS, UML, ERD, UI and architecture | G.D. Sekhula + All Members | 2026-09-19 | 2026-09-20 | Completed | 100 | Check terminology, fields, flows and approved requirements | Yes |  | Completed
U3-16 | Phase 2 | Activity 3.5 | Prepare Phase 2 presentation covering architecture, UML, sequences, ERD, UI, alignment and progress | All Members | 2026-09-19 | 2026-09-21 | Completed | 100 | Phase 2 presentation deck; insert current progress evidence | Yes |  | Completed
U3-17 | Phase 2 | Activity 3.5 | Prepare individual defence questions and ensure each member can explain their contribution | All Members | 2026-09-20 | 2026-09-22 | Completed | 100 | Individual defence preparation | Yes |  | Completed
U3-18 | Phase 2 | Activity 3.5 | Final Phase 2 submission package review and submission readiness check | All Members | 2026-09-22 | 2026-09-22 | Completed | 100 | Final checklist: SRS, diagrams, source links, .mpp, tracker, GitHub evidence | Yes |  | Completed
Formulas:
Progress Flag = IF([Task Description]="","",IF([Status]="Completed","Completed",IF([Status]="Blocked","Blocked",IF([Status]="Delayed","Delayed",IF(AND([Due Date]<>"",[Due Date]<TODAY(),[Status]<>"Completed"),"Overdue","On Track")))))

## Individual Contributions
Individual Contribution Record
Student Name | Student Number | Reporting Phase | Activity | Assigned Responsibility | Work Personally Completed | Date Completed | Hours Spent | Evidence / Link | Verified by Group | Verification Date | Notes
M.N Matla | 216009568 | Unit 1 / Phase 1 | Activity 1.1 | Project Lead / Stakeholder Contact | Identified and confirmed stakeholder. Organized the meeting and obtained signed agreement. | 17/08/2026 | 1.5 |  | Yes
S.M Nkosi | 222020350 | Unit 1 / Phase 1 | Activity 1.1 | Process Documentation | Documented the current manual process and problem statement. | 18/08/2026 | 2 |  | Yes
All Members |  | Unit 1 / Phase 1 | Activity 1.1 | Define project objectives | Defined the project aim, objectives, and scope sections of SRS | 19/08/2026 | 5 |  | Yes |  | -
G.D. Sekhula | 223028212 | Unit 1 / Phase 1 | Activity 1.2 | Interview Preparation | Prepared stakeholder interview questions. | 21/08/2026 | 2 |  | Yes |  | -
All Members |  | Unit 1 / Phase 1 | Activity 1.2 | Conduct Interview | Explained the purpose of the interview, asked questions, and recorded the stakeholder's responses. | 24/08/2026 | 0.5 |  | Yes |  | -
All Members |  | Unit 1 / Phase 1 | Activity 1.3 | SRS Preparation | Prepared the SRS sections | 25/08/2026 | 9 |  | Yes |  | -
T.H. Mosia | 222040802 | Unit 1 / Phase 1 | Activity 1.3 | Microsoft Project Schedule | Created the initial Microsoft Project schedule with all tasks, and timeline. | 26/08/2026 | 5 |  | Yes |  | -
L. Kayane | 222002417 | Unit 1 / Phase 1 | Activity 1.3 | Supabase Creation | Created Supabase project. | 26/08/2026 | 0.5 |  | Yes |  | -
L. Kayane | 222002417 | Unit 1 / Phase 1 | Activity 1.3 | GitHub Repository | Created and configured GitHub repository. Added README, invited members, and set up documentation folder. | 26/08/2026 | 1 |  | Yes
All Members |  | Unit 1 / Phase 1 | Activity 1.3 | Progress Workbook | Completed the Project Progress Workbook with all project details and evidence links. | 26/08/2026 | 3 |  | Yes
All Members |  | Unit 1 / Phase 1 | Activity 1.3 | Completed Group Reflection | Completed the group reflection | 26/08/2026 | 1 |  | Yes
All Members |  | Unit 1 / Phase 1 | Activity 1.3 | SRS Review | Completed the SRS document | 26/08/2026 | 2 |  | Yes
All Members |  | Unit 2 / Phase 1 | Activity 2.1 | Reviewing the current project |  | 27/08/2026 | 0.5 |  | Yes
L. Kayane | 222002417 | Unit 2 / Phase 1 | Activity 2.1 | Investigate technology and group skills (Technical feasibility) | Evaluated team's experience with Flutter and Supabase | 27/08/2026 | 0.5 |  | Yes
M.N Matla | 216009568 | Unit 2 / Phase 1 | Activity 2.1 | Analyze stakeholder and user environment (Operational feasibility) | Analyzed the stakeholder workflow at Lenyora Primary School | 27/08/2026 | 0.5 |  | Yes
S.M Nkosi | 222020350 | Unit 2 / Phase 1 | Activity 2.1 | Evaluate available resources (Econimic feasibility) | Confirmed use of free resources, no additional costs required | 27/08/2026 | 0.5 |  | Yes
T.H. Mosia | 222040802 | Unit 2 / Phase 1 | Activity 2.1 | Determine project timeline constraints (Schedule feasibility) | Prioritized Must-Have features for both mobile and website within the given timeline | 27/08/2026 | 0.5 |  | Yes
G.D. Sekhula | 223028212 | Unit 2 / Phase 1 | Activity 2.1 | Examine data privacy,POPIA compliance, and security rules (Legal feasibility) |  | 27/08/2026 | 0.5 |  | Yes
T.H. Mosia | 222040802 | Unit 2 / Phase 1 | Activity 2.1 | Review ethical implications and responsible use (Ethical feasibility) | Ensured simple UI for low digital literacy and responsible in handling data | 27/08/2026 | 0.5 |  | Yes
All Members |  | Unit 2 / Phase 1 | Activity 2.1 | Consolidate all feasibility areas and draft overall feasibility conclusion |  | 27/08/2026 | 0.5 |  | Yes
All Members |  | Unit 2 / Phase 1 | Activity 2.2 | Creating a project risk register | Identified the project risks and their impact, level and solutions | 28/08/2026 | 0.5 |  | Yes
M.N Matla |  | Unit 2 / Phase 1 | Activity 2.2 | Creating SWOT analysis | Created the SWOT for the project | 28/08/2026 | 0.5 |  | Yes
All Members |  | Unit 2 / Phase 1 | Activity 2.2 | Updating the SRS | Included feasibility findings, project risks and screenshot | 28/08/2026 | 0.5 |  | Yes
All Members |  | Unit 2 / Phase 1 | Activity 2.2 | Updating the Microsoft Project Schedule | Included feasibility tasks and project risks tasks | 28/08/2026 | 0.5 |  | Yes
All Members |  | Unit 2 / Phase 1 | Activity 2.2 | Complete the progress report and contribution record | Filled in tasks and recorded individual contributions | 28/08/2026 | 0.5 |  | Yes
T.H. Mosia | 222040802 | Unit 3 / Phase 2 | Activity 3.1 | Develop the system architecture diagram | Developed the system architecture diagram. | 08/09/2026 | 2 | Phase2_SRS_Insertion_and_Defence_Pack.docx / Phase 2 architecture material | Yes
T.H. Mosia | 222040802 | Unit 3 / Phase 2 | Activity 3.2 | Developing Use case diagram | Developed and completed the use case diagram. | 08/09/2026 | 1.5 | Phase2_SRS_Insertion_and_Defence_Pack.docx / Phase 2 use-case material | Yes
All Members |  | Unit 3 / Phase 2 | Activity 3.2 | Developing sequence diagram | Developed and completed the sequence-diagram material. | 09/09/2026 | 4 | Phase2_SRS_Insertion_and_Defence_Pack.docx / Phase 2 sequence material | Yes
L. Kayane | 222002417 | Unit 3 / Phase 2 | Activity 3.2 | Developing the database design | Developed the database design. | 10/09/2026 | 1 | https://venvbjsfuduuvbfigqva.supabase.co | Yes
All Members |  | Unit 3 / Phase 2 | Activity 3.2 | Developing the user interface | Developed the user interface | 17/09/2026 | 2 |  | Yes |  | Individual ownership and completion date should be confirmed before final submission; do not leave an All Members claim unsupported.
All Members |  | Unit 3 / Phase 2 | Activity 3.2 | Finalised the system design | Finalised the system design | 24/09/2026 | 1.5 |  | Yes |  | Final system design is still in progress; record each member’s actual contribution and evidence before marking complete.

## Stakeholder Engagement
Stakeholder Engagement Record
Date | Reporting Phase | Type of Engagement | Purpose | Students Present | Stakeholder Present / Role | Main Findings | Action Required | Evidence / Link
17/08/2026 | Phase 1 | Site Visit | Confirmed stakeholder and obtain letter of agreement. | M.N Matla | Head of department, Lenyora Primary School | School confirmed the need for a digital application system. Key features needed: online applications, announcements, subject listings, and status tracking. | Document the current process and problem statement.
24/08/2026 | Phase 1 | Meeting | Gather detailed requirements for the system. Understand stakeholder's needs. | All Members | Head of Department, Lenyora Primary School | Parents miss the opening and closing dates for the applications. Parents frequently ask about subjects per grade. Paper forms are often lost. | Preparing the SRS documentation

## Phase Summary
Phase Progress Summary
Summary Information | Group Response | Phase Completion Checklist
Reporting phase | Phase 2 | Initial or updated SRS completed | Yes
Reporting period | 08 September 2026 - 22 September 2026 | Progress report updated | Yes
Overall phase status | In Progress | Individual contributions recorded | Yes
What was completed during this phase? | Produced the system architecture design; developed UML use-case and sequence-diagram material; developed the initial ERD/database design; produced Flutter and ASP.NET interface designs; started design-alignment and evidence preparation. | Stakeholder engagement recorded | Yes
What remains incomplete? | Final consistency/requirements traceability checks, editable source register, Microsoft Project evidence, complete GitHub/tracker evidence, stakeholder/design review, final presentation and individual defence preparation. | Challenges and actions updated | Yes
Why is it incomplete? | These items require final group verification and evidence before submission. | Group reflection completed | No
Which contributions were particularly important? | Architecture and UML design; database/ERD design; mobile and administrator interface design; shared documentation and review work. | Microsoft Project updated | No
Were there participation concerns? | No final participation conclusion is recorded yet. Each member should complete genuine Phase 2 work and record personal evidence before the group marks participation as complete. | GitHub evidence available | Yes
What will the group improve in the next phase? | Use short technical check-ins, assign named owners to each outstanding artefact, and verify every completed item against evidence before submission. | Confidential peer check completed | No
Main priority for the next phase | Finalise and verify the complete Phase 2 design package and evidence trail.

## Challenges & Actions
Challenges and Corrective Actions
Date Identified | Reporting Phase | Challenge | Effect on Progress | Corrective Action | Responsible Student | Target Date | Status
21/08/2026 | Phase 1 | Our first stakeholder's needs did not align with our project requirements as per the module. | Slight delay in scheduling a meeting with the new stakeholder to collect the requirements. | Managed to schedule the meeting. | All members |  | Resolved
25/08/2026 | Phase 1 | Group member had technical issues with GitHub repository access. | Temporary block on collaborative work. | Re-sent invitation links and provided GitHub setup documentation. Verified access resolved. | L. Kayane |  | Resolved
26/08/2026 | Phase 1 | Misunderstanding about SRS formatting and structure requirements. | Required additional time to reformat document. | Reviewed sample SRS documents. Reorganized document structure accordingly. | S.M. Nkosi, G.D Sekhula |  | Resolved
25/08/2026 | Phase 1 | Used the online microsoft project for scheduling instead of the project professional app. | It was a slight setback as it took too much time to start the new one on the app. | We started scheduling using the project professional app. | T.H Mosia, M.N Matla |  | Resolved
22/09/2026 | Phase 2 | Several design artefacts still require final consistency checks and complete editable-source evidence. | Submission evidence is incomplete even though the main design artefacts exist. | Assign owners to the alignment matrix, source register, Microsoft Project evidence and final QA; verify each item before submission. | All members | 23/09/2026 | Resolved
22/09/2026 | Phase 2 | The current Supabase project URL must be confirmed as the project used by the Phase 2 implementation and documentation. | Inconsistent backend references could weaken architecture/ERD/configuration evidence. | Confirm the active project, then use the same project reference consistently in the SRS, README, tracker and implementation configuration. | L. Kayane, G.D. Sekhula | 24/09/2026 | Resolved

## Group Reflection
Group Reflection
Reflection Information | Group Response | Reflection Guidance
Reporting phase | Phase 2 | Length | Approximately 300–400 words in total.
Project title | Lenyora Primary School Digital Application System | Focus | Discuss the group’s actual experience, not the activity instructions.
Most important learning from this phase | The main learning in Phase 2 has been that the architecture, UML, database and interface designs must tell one consistent system story. The group has developed the main design artefacts and identified the need to trace requirements through use cases, sequences, database structures and interfaces before final submission. | Honesty | Identifying a genuine challenge will not disadvantage the group when an improvement action is provided.
What went well and why? | The group made progress on architecture, UML, database and interface design. Existing design material provides a basis for finalisation, while the remaining tasks focus on verification, traceability and submission evidence. | Evidence | Ensure that claims about participation agree with the contribution record, Microsoft Project and GitHub.
What was difficult and why? | Keeping all design artefacts consistent and completing the supporting evidence, especially editable source links, the updated Microsoft Project schedule, current GitHub/tracker evidence and final stakeholder/design review. | Research use | Student work may only be used for research after the required ethical approval and consent processes.
How were tasks divided among members? | Phase 2 responsibilities are being divided around the project roles: S.M. Nkosi supports documentation/project coordination; L. Kayane supports Flutter/Supabase work; G.D. Sekhula supports database/security/verification; T.H. Mosia supports architecture/UML/UI design; M.N. Matla supports the ASP.NET administrator portal. Each member must record only work they personally complete.
Did all members contribute fairly? Explain. | Final participation should be confirmed from actual task records, commits, design files, database work, reviews and other evidence. The tracker should not be used to create contribution claims that have not occurred.
How did the group handle disagreements or delays? | Use named owners, short group check-ins and peer review so that each artefact is verified before submission.
What did the group learn from the stakeholder? | Maintain a single source of truth for the architecture, UML, ERD and UI; verify the actual Supabase schema; and record evidence immediately after each member completes a task.
Improvement action 1 for the next phase | Complete the remaining Phase 2 evidence and final design QA.
Improvement action 2 for the next phase | Complete the source register and Microsoft Project/GitHub evidence, conduct final requirements traceability, then prepare all members for the defence.
Priority for the next phase | Final Phase 2 readiness and evidence verification