## Sheet1
Risk ID | Risk statement | Category | Likelihood (1–3) | Impact (1–3) | Score | Level | Mitigation | Contingency | Risk owner | Status
1 | Limited Supabase experience may delay backend integration | Technical | 2 | 3 | 6 | Medium | Assign specific learning tasks to the database designer and have them share the knowledge with the rest of the team | Simplify the functions affected by the integration, such as using file storage before implementing advanced features | GD Sekhula | Monitoring
2 | Stakeholder may become unavailable for feedback | Stakeholder | 2 | 1 | 2 | Low | Arrange key meetings and feedback dates early in the project | Request written feedback via email and use previously confirmed requirements | SM Nkosi | Monitoring
3 | Too many proposed functions may prevent the group from completing the prototype within the semester | Scope | 3 | 3 | 9 | High | Strictly prioritize the development of the "Must Have" functions | Remove lower priority functions from the project scope | TH Mosia | Monitoring
4 | A group member may not complete assigned tasks on time | Team | 2 | 3 | 6 | Medium | Allocate clear and specific tasks to each member with defined deadlines | Reassign urgent tasks to another member and record the issue in the project progress tracker | SM Nkosi | Open
5 | Development tasks may take longer than planned | Schedule | 2 | 3 | 6 | Medium | Create a detailed schedule with a realistic time estimate for each task | Prioritize "Must Have" features and be ready to postpone "Should Have" features | All Members | Open
6 | Internet connectivity may be unreliable for team members | Resource | 1 | 3 | 3 | Low | Ensure all team members have backup plans(e.g. use campus Wi-Fi or Mobile Data) | Use a mobile hotspot as a backup for our PC | L Kayane | Monitoring
7 | Data privacy or security oversight could expose personal information | Data & Security | 2 | 3 | 6 | Medium | Implement and strictly enforce Supabase Row Level Security policies | Notify the stakeholder immediately and restrict data access until the issue is resolved | MN Matla | Monitoring
8 | Inadequate testing may lead to a prototype with unresolved bugs | Quality | 2 | 2 | 4 | Medium | Plan for a dedicated testing period in the Microsoft Project Schedule | Postpone low priority features to create more time for testing bug fixes | GD Sekhula | Monitoring
9 | Users may struggle with lower digital literacy | Operational | 2 | 2 | 4 | Medium | Design the mobile app with a very simple guided user interface | Create a short, easy-to-understand user guide for the app | L Kayane | Monitoring
10 | Compatibility issues with different Android versions | Technical | 2 | 2 | 4 | Medium | Test the app on a range of Android emulators and physical devices covering the range API level (Android 8.0+) | Provide support for the most common Android versions first | MN Matla | Monitoring